## Instructions1
DUE DILIGENCE TRACKER - USER GUIDE
OVERVIEW
This Due Diligence Tracker is a comprehensive tool for managing the entire due diligence process for M&A, LBO, or investment transactions.
It integrates with the DCF and LBO valuation models to provide end-to-end deal analysis capabilities.
COLOR CODING SYSTEM
🔵 Blue text with yellow highlight = INPUT CELLS (your data)
⚫ Black text = FORMULAS (automatically calculated)
🟢 Green text = LINKS to other sheets
WORKSHEET GUIDE
1. EXECUTIVE SUMMARY
• Dashboard with key metrics and progress tracking
• Overall completion percentages
• Risk summary and go/no-go recommendation
• No inputs required - all automated from other sheets
2. MASTER CHECKLIST
• Comprehensive list of 162+ DD items across all workstreams
• Track Status, Priority, Owner, Due Dates
• Link to supporting documents
• Covers: Financial, Legal, Commercial, Operational, IT, ESG, HR
3. RISK ASSESSMENT
• Log all identified risks and issues
• Rate by Severity and Likelihood
• Auto-calculates Risk Rating (High/Medium/Low)
• Quantify impact in dollars
• Track mitigation plans
4. ACTION ITEMS
• Track all action items from DD process
• Link to related risks
• Monitor due dates and overdue items
• Update status as items progress
5. DOCUMENT REPOSITORY
• Log all documents requested and received
• Track document status and location
• Link to data room or file storage
6. TEAM TRACKER
• Maintain team member contact information
• Track workstream assignments
• Monitor active tasks per person
• Include external advisors and contacts
QUICK START (30 MINUTES)
Step 1: Enter transaction information in Executive Summary (5 min)
• Company name, deal value, dates, deal lead
Step 2: Review Master Checklist and customize (10 min)
• Add/remove items based on your transaction
• Assign owners and due dates
• Set priorities
Step 3: Add team members in Team Tracker (5 min)
• Internal team and external advisors
Step 4: Begin logging documents and tracking progress (10 min)
• Update statuses as items complete
• Log risks and action items as identified
INTEGRATION WITH OTHER MODELS
This DD Tracker is designed to work alongside:
• DCF Model - Use findings to refine valuation assumptions
• LBO Model - Identify risks affecting returns
• Merger Model - Track integration issues
Link key DD findings (revenue risks, cost synergies, etc.) to
your valuation models to create integrated deal analysis.
BEST PRACTICES
✓ Update status daily during active DD period
✓ Hold weekly team reviews of dashboard
✓ Flag high-priority and high-risk items immediately
✓ Document all findings in Notes columns
✓ Link related items (DD items → Risks → Actions)
✓ Maintain document repository religiously
✓ Export Executive Summary for IC memos
For questions or support, refer to the comprehensive DCF Model Guide
and LBO Model Guide included in your toolkit.

## Instructions
DUE DILIGENCE TRACKER - USER GUIDE
PURPOSE | This Due Diligence Tracker helps manage comprehensive DD across all workstreams for M&A transactions, LBOs, and strategic investments.
SHEETS OVERVIEW
1. Executive Summary | High-level dashboard showing overall progress, workstream status, and risk summary
2. Master Checklist | Comprehensive checklist of 150+ DD items across all categories
3. Financial DD Detail | Detailed financial due diligence items and findings
4. Legal DD Detail | Legal and regulatory DD items
5. Commercial DD Detail | Market, customer, and competitive analysis
6. Issue Log | Track all due diligence issues and red flags
7. Risk Register | Comprehensive risk assessment and mitigation
8. Document Tracker | Track all requested and received documents
9. Timeline & Milestones | Track key DD milestones and deadlines
10. Integration w/ Models | Links to DCF and LBO models
COLOR CODING
Blue text with yellow highlight
Black text
Green text
HOW TO USE
Step 1 | Enter deal information in Executive Summary
Step 2 | Update Master Checklist as you receive documents
Step 3 | Log any issues in Issue Log with severity
Step 4 | Track risks in Risk Register
Step 5 | Review Executive Summary dashboard for overall progress
INTEGRATION
This tracker is designed to integrate with your DCF and LBO models.
Key findings flow into valuation assumptions and risk adjustments.
See 'Integration w/ Models' sheet for linking instructions.

## Executive Summary
DUE DILIGENCE TRACKER - EXECUTIVE SUMMARY
DEAL INFORMATION |  |  |  |  | OVERALL PROGRESS
Target Company: | Enter Company Name |  |  |  | Total Items: | 140
Transaction Type: | LBO / Strategic / Minority |  |  |  | Completed: | 0
Deal Size ($M): | 0 |  |  |  | In Progress: | 0
DD Start Date: | 2025-10-29 10:41 |  |  |  | Not Started: | 0
Target Close Date: | 2025-12-28 10:41 |  |  |  | % Complete: | 0%
Days Remaining: | 60
Lead Partner: | Name
WORKSTREAM PROGRESS
Workstream | Total | Complete | In Progress | Not Started | % Done | Status
Financial DD | 0 | 0 | 0 | 0 | 0% | ✗
Legal & Regulatory | 0 | 0 | 0 | 0 | 0% | ✗
Commercial DD | 0 | 0 | 0 | 0 | 0% | ✗
Operational DD | 0 | 0 | 0 | 0 | 0% | ✗
IT / Technology | 0 | 0 | 0 | 0 | 0% | ✗
HR / Organization | 0 | 0 | 0 | 0 | 0% | ✗
Tax DD | 0 | 0 | 0 | 0 | 0% | ✗
Environmental | 0 | 0 | 0 | 0 | 0% | ✗
RISK & ISSUE SUMMARY
Risk Level | Count | Open Issues
High | 0 | 0
Medium | 0 | 0
Low | 0 | 0
KEY FINDINGS & RED FLAGS
Critical Issues: | 0
Deal Breakers: | 0 | 0

## Master Checklist
COMPREHENSIVE DUE DILIGENCE MASTER CHECKLIST
Instructions: Track all DD items. Update Status, Responsible Party. Flag issues in Issue Log. Color code: Blue = Input, Black = Formula, Green = Link
# | Category | Workstream | Item Description | Document/Data Required | Priority | Responsible | Due Date | Date Rcvd | Status | % Done | Risk | Notes
1 | I.A | Financial DD | Historical Financials | 5 years audited P&L, BS, CF | Critical |  |  |  | Not Started | 0%
2 | I.A | Financial DD | Monthly Financials | Latest 12 months unaudited | Critical |  |  |  | Not Started | 0%
3 | I.A | Financial DD | Quality of Earnings | Detailed QoE analysis with add-backs | Critical |  |  |  | Not Started | 0%
4 | I.A | Financial DD | Revenue by Customer | Customer concentration (3 years) | High |  |  |  | Not Started | 0%
5 | I.A | Financial DD | Revenue by Product | Product/service mix analysis | High |  |  |  | Not Started | 0%
6 | I.A | Financial DD | Revenue Recognition | ASC 606 policies and compliance | High |  |  |  | Not Started | 0%
7 | I.A | Financial DD | Recurring Revenue | MRR/ARR breakdown and retention | High |  |  |  | Not Started | 0%
8 | I.A | Financial DD | Backlog Analysis | Contracted not yet recognized | Medium |  |  |  | Not Started | 0%
9 | I.A | Financial DD | Working Capital | A/R, Inventory, A/P analysis | Critical |  |  |  | Not Started | 0%
10 | I.A | Financial DD | A/R Aging | Detailed receivables aging report | High |  |  |  | Not Started | 0%
11 | I.A | Financial DD | Bad Debt Reserve | Historical bad debt experience | Medium |  |  |  | Not Started | 0%
12 | I.A | Financial DD | Inventory Analysis | Raw, WIP, finished goods | High |  |  |  | Not Started | 0%
13 | I.A | Financial DD | Inventory Obsolescence | Slow-moving and obsolete reserve | Medium |  |  |  | Not Started | 0%
14 | I.A | Financial DD | A/P Aging | Vendor payment terms | Medium |  |  |  | Not Started | 0%
15 | I.A | Financial DD | Accrued Liabilities | Detail of all accruals | Medium |  |  |  | Not Started | 0%
16 | I.B | Financial DD | EBITDA Reconciliation | Normalized EBITDA calculation | Critical |  |  |  | Not Started | 0%
17 | I.B | Financial DD | Add-backs Support | Documentation for all add-backs | Critical |  |  |  | Not Started | 0%
18 | I.B | Financial DD | One-time Items | Non-recurring revenue/expenses | High |  |  |  | Not Started | 0%
19 | I.B | Financial DD | Related Party Trans | All RPTs and market rates | High |  |  |  | Not Started | 0%
20 | I.C | Financial DD | CapEx Analysis | Maintenance vs growth CapEx | High |  |  |  | Not Started | 0%
21 | I.C | Financial DD | Fixed Assets | Complete PP&E listing | Medium |  |  |  | Not Started | 0%
22 | I.C | Financial DD | D&A Schedule | Depreciation by asset class | Medium |  |  |  | Not Started | 0%
23 | I.C | Financial DD | Deferred CapEx | Deferred maintenance needs | High |  |  |  | Not Started | 0%
24 | I.D | Financial DD | Cash Flow Statement | Operating, investing, financing | Critical |  |  |  | Not Started | 0%
25 | I.D | Financial DD | Free Cash Flow | FCF calculation and conversion | Critical |  |  |  | Not Started | 0%
26 | I.D | Financial DD | Cash Conversion | Days cash cycle analysis | High |  |  |  | Not Started | 0%
27 | I.E | Financial DD | Budget vs Actual | Variance analysis (3 years) | High |  |  |  | Not Started | 0%
28 | I.E | Financial DD | Financial Plan | Management 3-5 year projections | Critical |  |  |  | Not Started | 0%
29 | I.E | Financial DD | KPIs | Key operational metrics | High |  |  |  | Not Started | 0%
30 | I.E | Financial DD | Seasonality | Monthly revenue/EBITDA patterns | Medium |  |  |  | Not Started | 0%
31 | II.A | Legal & Regulatory | Certificate of Inc | Current certificate + amendments | Critical |  |  |  | Not Started | 0%
32 | II.A | Legal & Regulatory | Bylaws | Current bylaws | Critical |  |  |  | Not Started | 0%
33 | II.A | Legal & Regulatory | Board Minutes | 3 years board minutes | High |  |  |  | Not Started | 0%
34 | II.A | Legal & Regulatory | Shareholder Minutes | 3 years shareholder minutes | High |  |  |  | Not Started | 0%
35 | II.B | Legal & Regulatory | Cap Table | Complete capitalization table | Critical |  |  |  | Not Started | 0%
36 | II.B | Legal & Regulatory | Stock Certificates | All outstanding certificates | High |  |  |  | Not Started | 0%
37 | II.B | Legal & Regulatory | Option Agreements | Stock option grants | High |  |  |  | Not Started | 0%
38 | II.B | Legal & Regulatory | Vesting Schedules | All vesting schedules | Medium |  |  |  | Not Started | 0%
39 | II.B | Legal & Regulatory | Shareholder Agreements | Voting, buy-sell agreements | High |  |  |  | Not Started | 0%
40 | II.B | Legal & Regulatory | Registration Rights | Any registration rights | Medium |  |  |  | Not Started | 0%
41 | II.C | Legal & Regulatory | Material Contracts | Contracts >$100K annual | Critical |  |  |  | Not Started | 0%
42 | II.C | Legal & Regulatory | Customer Contracts | Top 10 customer agreements | Critical |  |  |  | Not Started | 0%
43 | II.C | Legal & Regulatory | Supplier Contracts | Top 10 supplier agreements | High |  |  |  | Not Started | 0%
44 | II.C | Legal & Regulatory | Partnership Agreements | JVs and strategic partnerships | High |  |  |  | Not Started | 0%
45 | II.C | Legal & Regulatory | Distribution Agreements | Channel partner agreements | Medium |  |  |  | Not Started | 0%
46 | II.C | Legal & Regulatory | Licensing Agreements | Software and technology licenses | High |  |  |  | Not Started | 0%
47 | II.D | Legal & Regulatory | Pending Litigation | All pending lawsuits | Critical |  |  |  | Not Started | 0%
48 | II.D | Legal & Regulatory | Threatened Litigation | Demand letters, complaints | High |  |  |  | Not Started | 0%
49 | II.D | Legal & Regulatory | Litigation History | Settled cases (5 years) | Medium |  |  |  | Not Started | 0%
50 | II.D | Legal & Regulatory | Regulatory Investigations | Any regulatory inquiries | Critical |  |  |  | Not Started | 0%
51 | II.E | Legal & Regulatory | Insurance Policies | All current policies | High |  |  |  | Not Started | 0%
52 | II.E | Legal & Regulatory | Coverage Analysis | Coverage adequacy review | Medium |  |  |  | Not Started | 0%
53 | II.E | Legal & Regulatory | Claims History | 5 years claims history | Medium |  |  |  | Not Started | 0%
54 | II.F | Legal & Regulatory | Regulatory Licenses | Industry-specific permits | Critical |  |  |  | Not Started | 0%
55 | II.F | Legal & Regulatory | Compliance Programs | Compliance policies and training | High |  |  |  | Not Started | 0%
56 | III.A | Legal & Regulatory | Patent Portfolio | Patents granted and pending | Critical |  |  |  | Not Started | 0%
57 | III.A | Legal & Regulatory | Trademark Portfolio | Trademarks and registrations | High |  |  |  | Not Started | 0%
58 | III.A | Legal & Regulatory | Copyright Portfolio | Copyrighted materials | Medium |  |  |  | Not Started | 0%
59 | III.A | Legal & Regulatory | Trade Secrets | Trade secret protection measures | High |  |  |  | Not Started | 0%
60 | III.B | Legal & Regulatory | IP Licenses In | Third-party IP licenses | Critical |  |  |  | Not Started | 0%
61 | III.B | Legal & Regulatory | IP Licenses Out | Licenses granted to others | High |  |  |  | Not Started | 0%
62 | III.C | Legal & Regulatory | IP Assignments | Employee/contractor assignments | Critical |  |  |  | Not Started | 0%
63 | III.C | Legal & Regulatory | IP Non-Competes | Non-compete agreements | Medium |  |  |  | Not Started | 0%
64 | III.D | Legal & Regulatory | IP Litigation | IP disputes and litigation | Critical |  |  |  | Not Started | 0%
65 | III.D | Legal & Regulatory | Freedom to Operate | FTO analysis for products | High |  |  |  | Not Started | 0%
66 | IV.A | Commercial DD | Market Size | TAM, SAM, SOM analysis | Critical |  |  |  | Not Started | 0%
67 | IV.A | Commercial DD | Market Growth | Historical and projected growth | High |  |  |  | Not Started | 0%
68 | IV.A | Commercial DD | Market Trends | Industry trends and drivers | High |  |  |  | Not Started | 0%
69 | IV.A | Commercial DD | Market Share | Company position vs competitors | High |  |  |  | Not Started | 0%
70 | IV.B | Commercial DD | Competitive Landscape | Competitor analysis | Critical |  |  |  | Not Started | 0%
71 | IV.B | Commercial DD | Competitive Position | Strengths and weaknesses | Critical |  |  |  | Not Started | 0%
72 | IV.B | Commercial DD | Competitive Advantages | Sustainable differentiation | Critical |  |  |  | Not Started | 0%
73 | IV.B | Commercial DD | Barriers to Entry | Moats and defensibility | High |  |  |  | Not Started | 0%
74 | IV.C | Commercial DD | Customer List | Complete customer list with revenue | Critical |  |  |  | Not Started | 0%
75 | IV.C | Commercial DD | Customer Concentration | Top 10 customer dependency | Critical |  |  |  | Not Started | 0%
76 | IV.C | Commercial DD | Customer Contracts | Terms, pricing, renewals | High |  |  |  | Not Started | 0%
77 | IV.C | Commercial DD | Customer Retention | Churn and NRR analysis | Critical |  |  |  | Not Started | 0%
78 | IV.C | Commercial DD | Customer Satisfaction | NPS scores and surveys | High |  |  |  | Not Started | 0%
79 | IV.C | Commercial DD | Customer References | Reference calls | High |  |  |  | Not Started | 0%
80 | IV.D | Commercial DD | Product Portfolio | Products and services offered | High |  |  |  | Not Started | 0%
81 | IV.D | Commercial DD | Product Roadmap | Future development plans | High |  |  |  | Not Started | 0%
82 | IV.D | Commercial DD | Pricing Strategy | Pricing model and positioning | Critical |  |  |  | Not Started | 0%
83 | IV.E | Commercial DD | Sales Pipeline | Current pipeline and stages | Critical |  |  |  | Not Started | 0%
84 | IV.E | Commercial DD | Sales Metrics | CAC, LTV, payback period | High |  |  |  | Not Started | 0%
85 | IV.E | Commercial DD | Sales Process | Sales cycle and conversion rates | High |  |  |  | Not Started | 0%
86 | V.A | Operational DD | Org Chart | Complete organizational chart | High |  |  |  | Not Started | 0%
87 | V.A | Operational DD | Facility Locations | All facilities and offices | High |  |  |  | Not Started | 0%
88 | V.A | Operational DD | Real Estate Leases | All property leases | Critical |  |  |  | Not Started | 0%
89 | V.B | Operational DD | Manufacturing Process | Production process flow | High |  |  |  | Not Started | 0%
90 | V.B | Operational DD | Production Capacity | Utilization and scalability | High |  |  |  | Not Started | 0%
91 | V.B | Operational DD | Quality Control | QC processes and metrics | High |  |  |  | Not Started | 0%
92 | V.C | Operational DD | Supply Chain | Supplier relationships | Critical |  |  |  | Not Started | 0%
93 | V.C | Operational DD | Supplier Concentration | Key supplier dependencies | High |  |  |  | Not Started | 0%
94 | V.C | Operational DD | Supply Agreements | Key supplier contracts | High |  |  |  | Not Started | 0%
95 | V.D | Operational DD | Equipment List | Critical equipment and age | High |  |  |  | Not Started | 0%
96 | V.D | Operational DD | Equipment Condition | Condition assessment | Medium |  |  |  | Not Started | 0%
97 | V.D | Operational DD | Maintenance CapEx | Deferred maintenance | High |  |  |  | Not Started | 0%
98 | V.E | Operational DD | Health & Safety | OSHA compliance | Critical |  |  |  | Not Started | 0%
99 | V.E | Operational DD | Safety Incidents | Incident history and rates | High |  |  |  | Not Started | 0%
100 | V.E | Operational DD | Safety Training | Training programs | Medium |  |  |  | Not Started | 0%
101 | VI.A | IT / Technology | IT Infrastructure | Servers, networks, cloud | High |  |  |  | Not Started | 0%
102 | VI.A | IT / Technology | Software Systems | ERP, CRM, core systems | Critical |  |  |  | Not Started | 0%
103 | VI.A | IT / Technology | Software Licenses | All software licenses | High |  |  |  | Not Started | 0%
104 | VI.A | IT / Technology | IT Budget | Annual IT spend | Medium |  |  |  | Not Started | 0%
105 | VI.B | IT / Technology | Cybersecurity | Security policies and controls | Critical |  |  |  | Not Started | 0%
106 | VI.B | IT / Technology | Data Privacy | GDPR, CCPA compliance | Critical |  |  |  | Not Started | 0%
107 | VI.B | IT / Technology | Security Incidents | Breach history | Critical |  |  |  | Not Started | 0%
108 | VI.B | IT / Technology | Pen Testing | Recent penetration tests | High |  |  |  | Not Started | 0%
109 | VI.C | IT / Technology | Business Continuity | DR and backup plans | High |  |  |  | Not Started | 0%
110 | VI.C | IT / Technology | IT Roadmap | Planned IT investments | Medium |  |  |  | Not Started | 0%
111 | VI.C | IT / Technology | Technical Debt | Legacy system risks | Medium |  |  |  | Not Started | 0%
112 | VI.C | IT / Technology | IT Staff | IT team size and capabilities | Medium |  |  |  | Not Started | 0%
113 | VII.A | HR / Organization | Employee List | Complete employee roster | Critical |  |  |  | Not Started | 0%
114 | VII.A | HR / Organization | Headcount by Function | Department breakdown | High |  |  |  | Not Started | 0%
115 | VII.A | HR / Organization | Org Structure | Reporting relationships | High |  |  |  | Not Started | 0%
116 | VII.B | HR / Organization | Compensation Analysis | Salary benchmarking | High |  |  |  | Not Started | 0%
117 | VII.B | HR / Organization | Bonus Plans | Incentive plans | High |  |  |  | Not Started | 0%
118 | VII.B | HR / Organization | Benefits Programs | Health, 401k, benefits | Medium |  |  |  | Not Started | 0%
119 | VII.B | HR / Organization | Equity Plan | Stock option plan | Critical |  |  |  | Not Started | 0%
120 | VII.C | HR / Organization | Employment Agreements | Key employee contracts | Critical |  |  |  | Not Started | 0%
121 | VII.C | HR / Organization | Change in Control | CIC and retention agreements | High |  |  |  | Not Started | 0%
122 | VII.C | HR / Organization | Non-Competes | Non-compete agreements | High |  |  |  | Not Started | 0%
123 | VII.C | HR / Organization | Key Person Risk | Critical dependencies | Critical |  |  |  | Not Started | 0%
124 | VII.C | HR / Organization | Management Bios | Background and experience | High |  |  |  | Not Started | 0%
125 | VII.D | HR / Organization | Employee Handbook | HR policies | Medium |  |  |  | Not Started | 0%
126 | VII.D | HR / Organization | Employee Turnover | Attrition rates | High |  |  |  | Not Started | 0%
127 | VII.D | HR / Organization | Employee Litigation | Employment disputes | High |  |  |  | Not Started | 0%
128 | VIII.A | Tax DD | Tax Returns | Federal/state returns (3 years) | Critical |  |  |  | Not Started | 0%
129 | VIII.A | Tax DD | Tax Positions | Uncertain tax positions | High |  |  |  | Not Started | 0%
130 | VIII.B | Tax DD | Tax Audits | History of audits | High |  |  |  | Not Started | 0%
131 | VIII.B | Tax DD | Tax Attributes | NOLs, credits, carryforwards | Critical |  |  |  | Not Started | 0%
132 | VIII.C | Tax DD | Transfer Pricing | Related party documentation | High |  |  |  | Not Started | 0%
133 | VIII.C | Tax DD | Sales Tax | Sales tax compliance | High |  |  |  | Not Started | 0%
134 | VIII.D | Tax DD | Tax Structure | Entity structure | Critical |  |  |  | Not Started | 0%
135 | VIII.D | Tax DD | International Tax | Foreign operations | Medium |  |  |  | Not Started | 0%
136 | IX.A | Environmental | Phase I ESA | Environmental assessments | Critical |  |  |  | Not Started | 0%
137 | IX.A | Environmental | Environmental Permits | Air, water, waste permits | Critical |  |  |  | Not Started | 0%
138 | IX.B | Environmental | Compliance History | Violations and citations | High |  |  |  | Not Started | 0%
139 | IX.B | Environmental | Environmental Incidents | Spills, remediation | Critical |  |  |  | Not Started | 0%
140 | IX.C | Environmental | Environmental Liabilities | Known/potential liabilities | Critical |  |  |  | Not Started | 0%

## Integration with Models
INTEGRATION WITH DCF AND LBO MODELS
DD FINDINGS IMPACT ON VALUATION
Instructions:
1. Key DD findings should flow into DCF and LBO model assumptions
2. Adjust revenue growth, margins, CapEx, NWC based on DD discoveries
3. Factor in identified risks through scenario analysis
4. Update WACC or discount rate for risk profile changes
5. Reflect working capital adjustments in purchase price
KEY DD FINDINGS IMPACT TABLE
Finding Category | DD Finding | Impact on Valuation | Model Adjustment | Value Impact ($M)
Revenue | Customer concentration - top 3 = 60% | Increase revenue risk | Lower revenue growth by 2% | -10
EBITDA | One-time legal costs $2M | Add back to normalized EBITDA | Increase EBITDA by $2M | 20
Working Capital | A/R aging shows DSO at 75 days | Higher NWC requirement | Increase NWC by $5M | -5
CapEx | Deferred maintenance approximately $3M | One-time CapEx needed | Add $3M CapEx in Year 1 | -3
Risk | Patent litigation exposure | Increase discount rate | WACC +0.5% | -15
Total Value Impact from DD: | -13
LINKS TO MODELS
DCF Model Link: | [Link to DCF_Model_Comprehensive.xlsx]
LBO Model Link: | [Link to LBO_Model_Comprehensive.xlsx]
KEY ASSUMPTIONS TO UPDATE IN MODELS:
• Revenue Growth Rates (based on customer and market DD)
• EBITDA Margins (based on QoE analysis)
• Working Capital assumptions (based on NWC analysis)
• CapEx requirements (maintenance + growth)
• WACC or Discount Rate (based on risk assessment)
• Terminal Growth Rate (based on market outlook)
• Exit Multiple (based on comparable transactions)

## Document Repository
DOCUMENT REPOSITORY LOG
Instructions: Log all documents received during due diligence. Link to data room or file locations.
Doc ID | Workstream | Document Type | Document Name | Date Requested | Date Received | Requested By | Provided By | Location/Link | Notes

## Team Tracker
DUE DILIGENCE TEAM & CONTACTS
Instructions: Maintain list of all team members and external contacts involved in due diligence.
INTERNAL TEAM
Name | Role | Workstream | Email | Phone | Company | Active Tasks | Notes
| Deal Lead | Overall
| Financial Analyst | Financial DD
| Legal Counsel | Legal & Regulatory
EXTERNAL ADVISORS & CONTACTS
Firm/Company | Contact Name | Role | Workstream | Email | Phone | Engagement Date | Notes